## Janeczek
Working Hours
DATE | PHASE | TASK | ESTIMATION | ACTUAL | COMMENT
2015-01-26 | Dokumentation | Initialisierung des Projekts + Schreiben wesentlicher Dokumentation | 1:00 | 0:29 | Initial Step
2015-01-26 | Design | UML-Design Second Draft | 2:00 | 0:55 | Second Design Draft
2015-01-26 | Implementation | Implementing the functionality of the program | 5:00 | 0:30 | STILL ONGOING....
2015-02-12 | Implementation | Learning from examples | 0:30 | 1:00 | trying to get back into the code
SUM |  |  | 8:30 | 2:54

## Mair
Working Hours
DATE | PHASE | TASK | ESTIMATION | ACTUAL | COMMENT
2015-01-23 | Design | Erstellen eines UML-Designs | 1:00 | 0:45 | First Design Draft
2015-01-26 | Design | UML-Design Second Draft | 2:00 | 0:55 | Second Design Draft
2015-01-26 | Documentation | Requirementsanalyse, Designüberlegung | 0:50 | 0:30
2015-01-27 | Implementation | Erstellung erster Verschlüsselungsmethoden | 1:30 | 2:30
2015-02-12 | Implementation | Learning from examples | 0:30 | 1:00 | trying to get back into the code
SUM |  |  | 5:50 | 5:40

## SUM
Working Hours
| NAME | ESTIMATION | ACTUAL
| Janeczek | 8:30 | 2:54
| Mair | 5:50 | 5:40
| SUM | 14:20 | 8:34